## Лист1
Tasks | Estimate (hours) | Status
1. Connect NRF24, LCD to OrangePi One via SPI | 4 | 50%
2. Create chart, where describe modules architecture and interaction | 12 | Done
3. LCD SPI:
3.1. Sceleton | 16 | Done
3.2. Transmit/Receive methods | 16 | Done
3.3. Output text on display from file | 16
Testing | 48
4. NRF24 SPI: | 36
4.1. Sceleton | 16
4.2. Transmit/Receive methods | 60
4.3. IRQ | 16
4.4. Modes (receiver\transmiter) | 32
Total hours: | 272
Total days: | 34